## Slide 1: Development of machine learning models to process Electronic Health Records – Imputation Strategies
Week 17 Meeting, 13/2/2021

## Slide 4
Logistic Regression
Random Forest

## Slide 5: Deep learning
From inhospital_mortality_AutoencoderEncoding
From my notebook

## Slide 6
Although mean, joint, and itr_imputed have good results for classification, it does not follow the general trend and shape of the data

## Slide 7
It is obvious in quite a few cases KNN and deep learning is has a closer distribution to the original data

## Slide 8
-The more samples, the more steady and accurate the imputation

## Slide 9: Discussion
Should I be discussing in terms of imputation, achieving good performance should not be the only measure of success
As the aim of imputation is to fill missing data as closely as the original data
Measure of success
  Root mean squared error (increase the amount of missing values)
  Distribution (kl-divergence)
  Classification performance
  Masked data prediction (imputation accuracy)
    Should I be doing this at the imputation stage?
    But removing more missing data will only reduce the accuracy of imputation as it has less data to impute from?

## Slide 10: Comparing imputations

## Slide 12: Switching focus
Is it possible to switch focus to creating an extraction pipeline
Show feature iimportance and select import features only
Using feature selection on different imputed data to find corelation

## Slide 13: Feature importance analysis

## Slide 14: Plan for upcoming weeks
Jan 31- Feb 7: Create comparison metrics pipeline + Optimize models (make changes) + feature selection
Feb 7 – Feb 14: Look at extraction Pipeline + masked data prediction
  Finish introduction and background
Feb 14 – Feb 21: Add imputation methods if all models are optimized + Deep learning classification
  Finish Analysis/ requirements
Feb 21 – Feb 28: Design, Implementation
Feb 28 – Mar 7: Evaluation, Conclusion
Mar 7 - Mar 14: Complete First Draft 2 weeks before deadline